## Project Plan
S/N. | Activities
1 | Get Admin access to Existing Production Instance
2 | Prioritize projects to be migrated to test instance
2 | Analyze the existing projects/Space/Repository for Jira software/confluence/Mercurial
3 | Creation of Test Env - Backup & Restore of DB, Restoration of latest data for Jira Software
4 | Creation of Test Env - Backup & Restore of DB, Restoration of latest data for Confluence
5 | Creation of Test Env - Backup & Restore of DB, Restoration of latest data for GitHub
6 | Create New Cloud Instance For Test Migration and initiate cloud test instance
7 | Pre-migration Checklist action will be performed (test instance)
8 | Migration of data from test server to cloud test instance (test instance)
9 | Post migration checklist will be performed (Test instance)
10 | UAT of Cloud Migrated Data in Test Instance
11 | Preparations for Prod Migration such as communication to stakeholders, end users
12 | Production Migration - All products
13 | Post migration support, addressing user queries

## Project details
Project/Space | Key | JIRA Software/Confluence | Project lead | Last issue update | Issues | Actions | Priority
Sample1 | FDC | Confluence | Srividya | dd-mm-yyy | 1 | Do not migrate | Low
Sample2 | ARC | Software | Manish | dd-mm-yyy | 420 | Migrate | Already migrated

## Mercurial Repo details
Repository | Size | Priority | Actions
Sample Repo | 720MB | High | Do not migrate
Sample Repo2 | 30MB | Low | Migrate